# Campaign Intelligence — Implementation Plan

Frame-AI Platform • Production Execution Plan • Claude-Driven Development

# 1. Epics Overview

The implementation is organized into 12 epics. Each epic is a self-contained unit of work that delivers a usable capability. Epics are ordered to maximize early value while respecting technical dependencies.

| # | Epic | Phase | Est. Effort | Dependencies |
| --- | --- | --- | --- | --- |
| E1 | Foundation & Schema Extension | MVP | 3-4 days | None (first) |
| E2 | Permissions & Auth Middleware | MVP | 2-3 days | E1 |
| E3 | Platform Connections | MVP | 4-5 days | E1, E2 |
| E4 | Campaign CRUD & Builder | MVP | 5-6 days | E1, E2, E3 |
| E5 | Metrics Sync & Dashboard | MVP | 4-5 days | E3, E4 |
| E6 | Leads & Funnel | MVP | 3-4 days | E1, E4 |
| E7 | Alerts System | Phase 2 | 3-4 days | E5 |
| E8 | AI Analysis & Insights | Phase 2 | 4-5 days | E5, E7 |
| E9 | Reports & Exports | Phase 2 | 3-4 days | E5, E6 |
| E10 | Competitor Intelligence | Phase 2 | 3-4 days | E1, E8 |
| E11 | Automations Engine | Phase 3 | 4-5 days | E7, E8 |
| E12 | Optimization & Advanced AI | Phase 3 | 3-4 days | E8, E11 |

## 1.1 Total Effort Estimate

| Phase | Epics | Estimated Duration | Delivered Capabilities |
| --- | --- | --- | --- |
| MVP (Phase 1) | E1-E6 | 3-4 weeks | Connections, campaigns, metrics, leads, live dashboard |
| Phase 2 | E7-E10 | 2-3 weeks | Alerts, AI insights, reports, competitor intel |
| Phase 3 | E11-E12 | 1-2 weeks | Automations, optimization sweeps, advanced AI |
| Total | E1-E12 | 6-9 weeks | Full Campaign Intelligence system |

# 2. Epic Details & Features

## Epic 1: Foundation & Schema Extension

Goal: Extend the existing database schema, create service layer scaffolding, and set up the infrastructure for all subsequent epics without breaking existing functionality.

Phase: MVP — Must be first

Effort: 3-4 days

Risk Level: Medium (touching existing schemas)

### Features

| ID | Feature | Description | Files Modified/Created |
| --- | --- | --- | --- |
| E1.1 | Extend Campaign interface | Add 27 new fields to Campaign type (healthScore, platform, metrics, etc.) | src/lib/db/schema.ts |
| E1.2 | Extend Lead interface | Add 8 new fields (qualityScore, funnelStage, aiQualification, etc.) | src/lib/db/schema.ts |
| E1.3 | Extend ClientKnowledge interface | Add strategy, competitors, campaignSettings fields | src/lib/db/schema.ts |
| E1.4 | Extend ClientInsight interface | Add campaignId, confidence, actionable, autoApplicable fields | src/lib/db/schema.ts |
| E1.5 | Extend ClientFile interface | Add campaignId, creativeType, performanceData fields | src/lib/db/schema.ts |
| E1.6 | Create new Supabase tables | app_campaign_metrics, app_campaign_alerts, app_campaign_reports, app_platform_connections, app_audit_log, app_scheduled_jobs | Supabase migrations |
| E1.7 | Create SupabaseCrud instances | 6 new crud instances for new tables | src/lib/db/collections.ts |
| E1.8 | Migrate automation_rules | Move from JsonStore to app_automation_rules (SupabaseCrud) | src/lib/db/collections.ts + migration script |
| E1.9 | Service layer scaffolding | Create empty service files with interface stubs | src/lib/services/*.ts (12 files) |
| E1.10 | Event bus setup | Create EventBus with typed EventMap | src/lib/events/event-bus.ts, types.ts |
| E1.11 | Database indexes | Create all indexes for new tables | Supabase migration |
| E1.12 | Utility modules | circuit-breaker.ts, rate-limiter.ts, retry.ts | src/lib/utils/ |

### Acceptance Criteria

All existing tests pass (no breaking changes)

New tables exist in Supabase with proper indexes

TypeScript compiles with no errors after schema extensions

Existing Campaign/Lead CRUD still works with old data (new fields are optional)

automation_rules migration script runs idempotently

## Epic 2: Permissions & Auth Middleware

Goal: Implement the role-based access control system with 10 roles, action-level permissions, and audit logging foundation.

Phase: MVP

Effort: 2-3 days

Depends On: E1 (User schema extension)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E2.1 | Role type extension | Extend User.role to support 10 new role values | src/lib/db/schema.ts |
| E2.2 | Permission matrix | Define ROLE_PERMISSIONS constant mapping roles to action→scope | src/lib/auth/permissions.ts |
| E2.3 | authorize() middleware | Permission resolver: role + ownership check per request | src/lib/auth/authorize.ts |
| E2.4 | Legacy role compatibility | getLegacyRole() mapper for backward compat with existing code | src/lib/auth/authorize.ts |
| E2.5 | API route protection | Middleware for /api/* routes (session check, cron secret, webhook sig) | src/middleware.ts |
| E2.6 | Audit service (core) | AuditService.log() with category, action, entity, user, result | src/lib/services/audit.service.ts |
| E2.7 | Audit API routes | GET /api/audit (admin query), GET /api/audit/export | src/app/api/audit/ |
| E2.8 | Client role isolation | Hard clientId check for client_viewer / client_limited_viewer | src/lib/auth/authorize.ts |
| E2.9 | User management API | CRUD users with role assignment + assignedClients | src/app/api/users/ |
| E2.10 | Role migration script | Migrate existing users: admin→admin, manager→campaign_manager, agent→campaign_manager | scripts/migrate-roles.ts |

### Acceptance Criteria

Existing users retain access (legacy role mapping works)

New roles can be assigned via API

Permission denied returns 403 with audit trail

Client roles cannot access other clients' data

Admin can query audit log

## Epic 3: Platform Connections

Goal: Enable OAuth connections to Meta, Google, TikTok, and LinkedIn ad platforms with token management and health monitoring.

Phase: MVP

Effort: 4-5 days

Depends On: E1 (tables), E2 (auth)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E3.1 | Connection API routes | CRUD + refresh + test endpoints | src/app/api/connections/ |
| E3.2 | ConnectionService | OAuth flow orchestration, token storage, health checks | src/lib/services/connection.service.ts |
| E3.3 | Meta OAuth integration | Facebook/Instagram OAuth flow, token exchange, account fetch | src/lib/platforms/meta/client.ts |
| E3.4 | Google Ads OAuth | Google OAuth flow, MCC account selection | src/lib/platforms/google/client.ts |
| E3.5 | TikTok OAuth | TikTok Business OAuth flow | src/lib/platforms/tiktok/client.ts |
| E3.6 | LinkedIn OAuth | LinkedIn Marketing OAuth flow | src/lib/platforms/linkedin/client.ts |
| E3.7 | Base platform interface | Abstract platform interface (connect, refresh, test, fetchMetrics) | src/lib/platforms/base-platform.ts |
| E3.8 | Token encryption | pgcrypto-based token encryption/decryption helpers | src/lib/utils/crypto.ts |
| E3.9 | Connection health cron | /api/cron/connection-health (every 6 hours) | src/app/api/cron/connection-health/ |
| E3.10 | Connections UI | Connections screen: list, add modal, status badges, health indicators | src/app/(dashboard)/connections/ |
| E3.11 | Client connections tab | Connections tab in client detail page | src/components/clients/tabs/TabConnections.tsx |

## Epic 4: Campaign CRUD & Builder

Goal: Full campaign lifecycle: create (wizard), edit, publish to platform, pause/resume, duplicate, archive.

Phase: MVP

Effort: 5-6 days

Depends On: E1, E2, E3 (needs active connections to publish)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E4.1 | Campaign API routes | Full CRUD + publish + duplicate + optimize endpoints | src/app/api/campaigns/ |
| E4.2 | CampaignService | Business logic: status transitions, validation, platform publish | src/lib/services/campaign.service.ts |
| E4.3 | Campaign Builder wizard | 4-step wizard UI: client/type → details → creative → review | src/app/(dashboard)/campaigns/new/ |
| E4.4 | Campaign list view | Filterable/sortable campaign grid with health scores | src/app/(dashboard)/campaigns/ |
| E4.5 | Campaign detail view | Full detail page: metrics, timeline, insights, alerts sections | src/app/(dashboard)/campaigns/[id]/ |
| E4.6 | Platform publish integration | Push campaign config to Meta/Google/TikTok/LinkedIn API | src/lib/platforms/*/campaigns.ts |
| E4.7 | Campaign status machine | Draft → scheduled → active → paused → completed → archived | src/lib/services/campaign.service.ts |
| E4.8 | Budget approval flow | If budget > threshold: status → pending_approval → notification | src/lib/services/campaign.service.ts |
| E4.9 | Client campaigns tab | Campaigns tab in client detail page | src/components/clients/tabs/TabCampaigns.tsx |
| E4.10 | Command Center dashboard | Agency-wide KPI row + campaign cards with health indicators | src/app/(dashboard)/page.tsx (modify) |
| E4.11 | Campaign audit events | Emit audit events for all campaign operations | Integrated in CampaignService |

## Epic 5: Metrics Sync & Dashboard

Goal: Automatically pull metrics from connected platforms, normalize, store, and display in real-time dashboard.

Phase: MVP

Effort: 4-5 days

Depends On: E3 (connections), E4 (campaigns)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E5.1 | MetricsService | Fetch, normalize, aggregate, store metric snapshots | src/lib/services/metrics.service.ts |
| E5.2 | Meta metrics normalization | Map Meta API fields to normalized schema | src/lib/platforms/meta/metrics.ts |
| E5.3 | Google metrics normalization | Map Google Ads API fields | src/lib/platforms/google/metrics.ts |
| E5.4 | TikTok metrics normalization | Map TikTok Business API fields | src/lib/platforms/tiktok/metrics.ts |
| E5.5 | LinkedIn metrics normalization | Map LinkedIn Marketing API fields | src/lib/platforms/linkedin/metrics.ts |
| E5.6 | Metrics sync cron | /api/cron/metrics-sync (every 15 min), cursor-based chunking | src/app/api/cron/metrics-sync/ |
| E5.7 | Health score computation | Daily cron + incremental updates on sync | src/lib/services/campaign.service.ts |
| E5.8 | Health scores cron | /api/cron/health-scores (daily 03:00) | src/app/api/cron/health-scores/ |
| E5.9 | Metrics API endpoint | GET /api/campaigns/[id]/metrics with date range | src/app/api/campaigns/[id]/metrics/ |
| E5.10 | Dashboard metrics display | Real-time KPIs, trend charts, spend pacing bars | Components in campaigns/[id]/ |
| E5.11 | Rate limiting per platform | Implement rate limiter respecting platform quotas | src/lib/utils/rate-limiter.ts |
| E5.12 | Vercel cron config | vercel.json crons setup for all MVP jobs | vercel.json |

## Epic 6: Leads & Funnel

Goal: Ingest leads from platforms, deduplicate, display Kanban funnel, enable status management and conversion tracking.

Phase: MVP

Effort: 3-4 days

Depends On: E1 (schema), E4 (campaigns exist)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E6.1 | LeadService | Ingest, dedup, normalize, qualify, funnel transitions | src/lib/services/lead.service.ts |
| E6.2 | Lead API routes | CRUD + sync + qualify + funnel + export | src/app/api/leads/ |
| E6.3 | Lead sync cron | /api/cron/lead-sync (every 10 min) | src/app/api/cron/lead-sync/ |
| E6.4 | Meta lead webhook | Inbound webhook for Meta Lead Ads real-time delivery | src/app/api/webhooks/meta/leads/ |
| E6.5 | Platform lead extraction | Extract lead form data from Meta/Google APIs | src/lib/platforms/*/leads.ts |
| E6.6 | Leads Kanban UI | Drag-and-drop funnel board (New → Contacted → Qualified → Proposal → Converted/Lost) | src/app/(dashboard)/leads/ |
| E6.7 | Lead detail drawer | Slide-out panel: contact info, form data, AI score, history | src/components/leads/LeadDrawer.tsx |
| E6.8 | Lead export | Export to CSV/XLSX with configurable columns | src/app/api/leads/export/ |
| E6.9 | Client leads tab | Leads tab in client detail page (filtered to client) | src/components/clients/tabs/TabLeads.tsx (modify existing) |
| E6.10 | Funnel analytics | Conversion rates per stage, time-in-stage, drop-off analysis | src/app/api/leads/funnel/ |

## Epic 7: Alerts System

Goal: Threshold-based alerting with severity levels, notification dispatch, escalation, and alert management UI.

Phase: Phase 2

Effort: 3-4 days

Depends On: E5 (metrics to evaluate against)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E7.1 | AlertService | Threshold evaluation, alert creation, cooldown management, escalation | src/lib/services/alert.service.ts |
| E7.2 | NotificationService | Multi-channel dispatch: in-app, email, push. Batching + preferences. | src/lib/services/notification.service.ts |
| E7.3 | Alerts check cron | /api/cron/alerts-check (every 5 min) | src/app/api/cron/alerts-check/ |
| E7.4 | Alert API routes | List, acknowledge, resolve, snooze + alert rules management | src/app/api/alerts/ |
| E7.5 | Alerts Center UI | Alert list with severity filtering, detail panel, action buttons | src/app/(dashboard)/alerts/ |
| E7.6 | In-app notifications | Bell icon with badge count, notification dropdown, mark-as-read | src/components/layout/Notifications.tsx |
| E7.7 | Email notifications | Transactional email templates for alert severity levels | src/lib/email/templates/ |
| E7.8 | Default threshold setup | Auto-create default alert rules when campaign is published | src/lib/services/alert.service.ts |
| E7.9 | Alert escalation | Auto-escalate unacknowledged critical alerts after 30 min | src/lib/services/alert.service.ts |
| E7.10 | Campaign alert badges | Show alert count/severity on campaign cards and detail view | Components update |

## Epic 8: AI Analysis & Insights

Goal: GPT-4o powered analysis generating actionable insights, optimization suggestions, and creative analysis.

Phase: Phase 2

Effort: 4-5 days

Depends On: E5 (metrics data), E7 (alerts for high-impact insights)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E8.1 | AIService | OpenAI integration, prompt management, response parsing | src/lib/services/ai.service.ts |
| E8.2 | OpenAI client wrapper | Rate limiting, error handling, model selection, cost tracking | src/lib/ai/openai-client.ts |
| E8.3 | Prompt templates | Versioned prompts for each analysis type | src/lib/ai/prompts/*.ts |
| E8.4 | AI analysis cron | /api/cron/ai-analysis (daily 04:00) | src/app/api/cron/ai-analysis/ |
| E8.5 | Optimization sweep cron | /api/cron/optimization-sweep (08:00, 18:00) | src/app/api/cron/optimization-sweep/ |
| E8.6 | Insight API routes | List, apply, dismiss, generate endpoints | src/app/api/insights/ |
| E8.7 | AI API routes | analyze-creative, predict-performance, generate-copy | src/app/api/ai/ |
| E8.8 | Insights UI | Insight cards with confidence, context, action buttons | src/app/(dashboard)/insights/ |
| E8.9 | Insight application | Execute recommendations via platform APIs + audit + follow-up | src/lib/services/ai.service.ts |
| E8.10 | Follow-up validation | After 48h, compare predicted vs actual metrics | src/lib/services/ai.service.ts |
| E8.11 | Client insights tab | Insights tab in client detail (filtered to client) | src/components/clients/tabs/TabInsights.tsx |
| E8.12 | AI copy generation UI | In campaign builder: generate variations button + picker | Campaign builder integration |

## Epic 9: Reports & Exports

Goal: Automated and on-demand report generation (PDF/XLSX) with AI summaries and client portal delivery.

Phase: Phase 2

Effort: 3-4 days

Depends On: E5 (metrics), E6 (lead data for lead reports)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E9.1 | ReportService | Template resolution, data aggregation, rendering, storage | src/lib/services/report.service.ts |
| E9.2 | Report generation cron | /api/cron/report-generation (Monday 07:00) | src/app/api/cron/report-generation/ |
| E9.3 | PDF rendering | Server-side PDF generation with @react-pdf/renderer | src/lib/reports/pdf-renderer.ts |
| E9.4 | XLSX rendering | Excel report generation with xlsx library | src/lib/reports/xlsx-renderer.ts |
| E9.5 | Report API routes | List, generate, download, schedule, portal toggle | src/app/api/reports/ |
| E9.6 | Reports UI | Report list, inline preview, download, share controls | src/app/(dashboard)/reports/ |
| E9.7 | Report templates | Weekly Performance, Monthly Executive, Lead Report, etc. | src/lib/reports/templates/ |
| E9.8 | AI report summaries | Call AIService for executive summary per report | Integration with E8 |
| E9.9 | Portal visibility | Toggle reports visible in client portal tab | Portal integration |
| E9.10 | Supabase Storage upload | Store generated reports in project-files bucket | src/lib/services/report.service.ts |
| E9.11 | Client reports tab | Reports tab in client detail page | src/components/clients/tabs/TabReports.tsx |

## Epic 10: Competitor Intelligence

Goal: Automated competitor ad scanning, change detection, alerting, and strategic response tools.

Phase: Phase 2

Effort: 3-4 days

Depends On: E1 (ClientKnowledge schema), E8 (AI for trend analysis)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E10.1 | CompetitorService | Scan orchestration, change detection, trend analysis | src/lib/services/competitor.service.ts |
| E10.2 | Meta Ad Library integration | Fetch active ads by page_id, extract creative data | src/lib/platforms/meta/ad-library.ts |
| E10.3 | Competitor scan cron | /api/cron/competitor-scan (daily 06:00) | src/app/api/cron/competitor-scan/ |
| E10.4 | Competitor API routes | List, update, scan, ads, trends endpoints | src/app/api/competitors/ |
| E10.5 | Competitor UI | Competitor grid, detail panel, ad gallery, trend charts | src/app/(dashboard)/competitors/ |
| E10.6 | Change detection | Diff current vs previous scan, generate change events | src/lib/services/competitor.service.ts |
| E10.7 | Competitor alerts | Auto-generate alerts on significant competitor changes | Integration with E7 |
| E10.8 | AI competitive analysis | AI summary of competitor shifts + recommended responses | Integration with E8 |
| E10.9 | Client competitor tab | Competitor Intelligence tab in client detail | src/components/clients/tabs/TabCompetitors.tsx |
| E10.10 | "Respond" actions | CTA buttons linking to campaign builder with competitive context | UI integration with E4 |

## Epic 11: Automations Engine

Goal: Rule-based automation system: create rules, test with dry-run, execute (or queue for approval), track history.

Phase: Phase 3

Effort: 4-5 days

Depends On: E7 (alerts as trigger source), E8 (insights as trigger source)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E11.1 | AutomationService | Rule evaluation, condition matching, action execution, history | src/lib/services/automation.service.ts |
| E11.2 | Rule builder API | CRUD + activate/deactivate + test + approve endpoints | src/app/api/automations/ |
| E11.3 | Automation evaluation | Triggered by events + cron; evaluate conditions against live data | src/lib/services/automation.service.ts |
| E11.4 | Dry-run testing | Run rule against last 7 days of data without executing | src/app/api/automations/[id]/test/ |
| E11.5 | Approval queue | Pending execution queue for require-approval rules | src/lib/services/automation.service.ts |
| E11.6 | Automation UI | Rule list, builder form, test results, execution history | src/app/(dashboard)/automations/ |
| E11.7 | Event-triggered evaluation | Subscribe to EventBus events and evaluate matching rules | src/lib/events/handlers/automation-events.ts |
| E11.8 | Platform action execution | Execute actions on platform APIs (pause ad set, adjust budget) | src/lib/platforms/*/actions.ts |
| E11.9 | Execution history | Log every rule trigger, decision, and action outcome | Via audit log + automation history |
| E11.10 | Client automations tab | Automations tab in client detail page | src/components/clients/tabs/TabAutomations.tsx |

## Epic 12: Optimization & Advanced AI

Goal: Twice-daily optimization sweeps, performance predictions, cross-campaign learning, budget allocation AI.

Phase: Phase 3

Effort: 3-4 days

Depends On: E8 (AI service), E11 (automations for auto-execute)

| ID | Feature | Description | Files |
| --- | --- | --- | --- |
| E12.1 | Optimization sweep logic | 7 optimization categories evaluated per campaign | src/lib/services/ai.service.ts |
| E12.2 | Auto-applicable suggestions | Link high-confidence suggestions to automation rules | Integration E8 + E11 |
| E12.3 | Budget allocation AI | Cross-platform budget distribution recommendations | src/lib/ai/prompts/budget-allocation.ts |
| E12.4 | Creative fatigue detection | CTR decline analysis + rotation suggestions | src/lib/ai/prompts/creative-analysis.ts |
| E12.5 | Audience saturation detection | Frequency analysis + expansion recommendations | Integrated in optimization sweep |
| E12.6 | Performance prediction API | /api/ai/predict-performance endpoint | src/app/api/ai/predict-performance/ |
| E12.7 | Cross-campaign learning | Identify patterns across all client campaigns | src/lib/ai/prompts/cross-campaign.ts |
| E12.8 | Feedback loop | Track prediction accuracy; improve prompts based on outcomes | src/lib/services/ai.service.ts |
| E12.9 | Strategy impact simulation | Predict impact of strategy changes on active campaigns | Integration with client strategy tab |
| E12.10 | Weekly cleanup cron | /api/cron/cleanup (Sunday 02:00) | src/app/api/cron/cleanup/ |

# 3. Epic Dependency Map

┌─────────────────────────────────────────────────────────────────────────┐
│                           DEPENDENCY GRAPH                              │
├─────────────────────────────────────────────────────────────────────────┤
│                                                                         │
│  ┌──────────┐                                                           │
│  │  E1      │ Foundation & Schema                                       │
│  │  (FIRST) │                                                           │
│  └────┬─────┘                                                           │
│       │                                                                 │
│       ├──────────────────────────┐                                      │
│       │                          │                                      │
│  ┌────▼─────┐              ┌─────▼────┐                                 │
│  │  E2      │              │  E6      │                                 │
│  │  Perms   │              │  Leads   │                                 │
│  └────┬─────┘              └─────┬────┘                                 │
│       │                          │                                      │
│  ┌────▼─────┐                    │         ┌────────────┐               │
│  │  E3      │                    │         │  E9        │               │
│  │  Connect │                    └────────▶│  Reports   │               │
│  └────┬─────┘                              └────────────┘               │
│       │                                                                 │
│  ┌────▼─────┐                                                           │
│  │  E4      │                                                           │
│  │  Campaigns│                                                          │
│  └────┬─────┘                                                           │
│       │                                                                 │
│  ┌────▼─────┐                                                           │
│  │  E5      │ Metrics Sync                                              │
│  └────┬─────┘                                                           │
│       │                                                                 │
│       ├──────────────────────┐                                          │
│       │                      │                                          │
│  ┌────▼─────┐          ┌────▼─────┐                                    │
│  │  E7      │          │  E10     │                                    │
│  │  Alerts  │          │  Compete │                                    │
│  └────┬─────┘          └──────────┘                                    │
│       │                                                                 │
│  ┌────▼─────┐                                                           │
│  │  E8      │ AI & Insights                                             │
│  └────┬─────┘                                                           │
│       │                                                                 │
│  ┌────▼─────┐                                                           │
│  │  E11     │ Automations                                               │
│  └────┬─────┘                                                           │
│       │                                                                 │
│  ┌────▼─────┐                                                           │
│  │  E12     │ Optimization & Advanced AI                                │
│  └──────────┘                                                           │
│                                                                         │
└─────────────────────────────────────────────────────────────────────────┘

## 3.1 Critical Path

The longest dependency chain determines minimum calendar time:

E1 (3d) → E2 (2d) → E3 (4d) → E4 (5d) → E5 (4d) → E7 (3d) → E8 (4d) → E11 (4d) → E12 (3d)
Critical path total: ~32 days (sequential)
With parallelism (E6 parallel to E3-E5, E9-E10 parallel to E7-E8): ~22-25 days

## 3.2 Parallelizable Work

| Parallel Track A | Parallel Track B | Can Start After |
| --- | --- | --- |
| E3 (Connections) | E6 (Leads — schema only, sync after E4) | E1 + E2 complete |
| E7 (Alerts) | E9 (Reports) + E10 (Competitors) | E5 complete |
| E11 (Automations) | E12 features that don't need E11 | E8 complete |

# 4. MVP Phase — Build Order

MVP delivers a working campaign management system with live metrics. After MVP, the team can create campaigns, sync metrics, and manage leads — the core daily workflow.

## 4.1 Week 1: Infrastructure

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 1 | E1 | Schema extensions + new tables | All interfaces extended; 6 new tables created; indexes applied |
| 2 | E1 | Service scaffolding + event bus + utilities | 12 service stubs; EventBus working; retry/circuit-breaker utils |
| 3 | E1 → E2 | Finish E1 (migration scripts) + start permissions | automation_rules migrated; role types defined |
| 4 | E2 | Permission matrix + authorize() middleware | ROLE_PERMISSIONS constant; middleware protecting routes |
| 5 | E2 | Audit service + legacy compat + role migration | Audit logging operational; existing users migrated to new roles |

## 4.2 Week 2: Connections & Campaigns

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 6 | E3 | Base platform interface + Meta OAuth | Meta connection flow working end-to-end |
| 7 | E3 | Google + TikTok + LinkedIn OAuth | All 4 platforms connectable |
| 8 | E3 | Connections UI + health cron + client tab | Connections screen usable; health monitoring active |
| 9 | E3 → E4 | Finish connections + campaign API routes | Connection APIs complete; campaign CRUD backend |
| 10 | E4 | CampaignService + status machine + publish | Campaign lifecycle working; can publish to platforms |

## 4.3 Week 3: Campaign UI & Metrics

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 11 | E4 | Campaign Builder wizard (UI) | 4-step wizard functional |
| 12 | E4 | Campaign list + detail views + Command Center | Campaign dashboard usable |
| 13 | E4 → E5 | Finish campaign UI + start MetricsService | Campaigns complete; metrics normalization working |
| 14 | E5 | Metrics sync cron + health scores | Metrics pulling every 15 min; health scores computing |
| 15 | E5 | Metrics display + charts + vercel.json crons | Dashboard showing real metrics; all crons configured |

## 4.4 Week 4: Leads & Polish

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 16 | E6 | LeadService + sync + dedup + Meta webhook | Leads flowing in from platforms |
| 17 | E6 | Leads Kanban UI + detail drawer | Lead management interface functional |
| 18 | E6 | Funnel analytics + export + client tab | Full lead pipeline visible |
| 19 | MVP polish | Bug fixes, edge cases, UX polish | MVP stable |
| 20 | MVP polish | End-to-end testing, deployment prep | MVP ready for production |

## 4.5 MVP Definition of Done

User can connect a Meta/Google ad account

User can create a campaign via wizard and publish to platform

Metrics sync every 15 minutes with normalized dashboard display

Health scores computed and displayed on campaign cards

Leads ingested from platforms and manageable in Kanban view

All operations protected by role-based permissions

Audit trail records all significant actions

Command Center shows agency-wide KPIs

Client detail page has Campaigns, Leads, and Connections tabs

No regression in existing Frame-AI functionality

# 5. Phase 2 — Build Order

Phase 2 adds intelligence layers: alerts, AI analysis, automated reports, and competitor monitoring. This transforms the system from operational tooling to a smart campaign management platform.

## 5.1 Week 5: Alerts

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 21 | E7 | AlertService + threshold evaluation + default rules | Alert engine evaluating metrics against thresholds |
| 22 | E7 | NotificationService + email templates + in-app | Notifications dispatching on alert fire |
| 23 | E7 | Alerts check cron + escalation logic | 5-minute cron running; escalation working |
| 24 | E7 | Alerts Center UI + campaign alert badges | Full alert management interface |

## 5.2 Week 6: AI & Insights

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 25 | E8 | AIService + OpenAI client + prompt templates | AI infrastructure operational |
| 26 | E8 | AI analysis cron + optimization sweep cron | Daily analysis running; twice-daily sweeps active |
| 27 | E8 | Insight API + apply/dismiss + follow-up validation | Insights actionable from API |
| 28 | E8 | Insights UI + AI copy generation in builder | Insight cards visible; AI copy assist working |
| 29 | E8 | Client insights tab + creative analysis | AI fully integrated into client workflow |

## 5.3 Week 7: Reports & Competitors

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 30 | E9 | ReportService + PDF/XLSX rendering | Reports generating correctly |
| 31 | E9 | Report cron + templates + AI summaries | Weekly reports auto-generating with AI summary |
| 32 | E9 | Reports UI + portal visibility + client tab | Full report workflow end-to-end |
| 33 | E10 | CompetitorService + Meta Ad Library integration | Competitor scanning working |
| 34 | E10 | Competitor scan cron + change detection + UI | Competitor intelligence dashboard live |
| 35 | E10 | Competitor alerts + AI analysis + client tab | Competitive intelligence fully integrated |

## 5.4 Phase 2 Definition of Done

Alerts fire within 5 minutes of threshold breach

Notifications delivered via in-app + email based on severity

Critical alerts escalate after 30 min without acknowledgment

AI generates performance insights daily with confidence scores

Optimization sweep runs at 08:00 and 18:00 with actionable suggestions

Users can apply AI recommendations with one click (+ follow-up tracking)

Weekly reports auto-generate and are downloadable as PDF

Client portal shows portal-visible reports

Competitor scans run daily with change detection alerts

All Phase 2 features respect permission matrix

# 6. Phase 3 — Build Order

Phase 3 adds autonomous capabilities: automations that act without human intervention (when configured), and advanced AI that learns from outcomes. This is the "smart autopilot" layer.

## 6.1 Week 8: Automations

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 36 | E11 | AutomationService + rule builder API + condition engine | Rule evaluation working |
| 37 | E11 | Dry-run testing + approval queue | Rules testable and approvable |
| 38 | E11 | Platform action execution + event subscriptions | Rules executing actions on platforms |
| 39 | E11 | Automations UI + execution history | Full automation management interface |
| 40 | E11 | Client automations tab + edge cases | Automations integrated into client workflow |

## 6.2 Week 9: Advanced Optimization

| Day | Epic | Focus | Deliverable |
| --- | --- | --- | --- |
| 41 | E12 | Auto-applicable suggestions + automation linking | AI suggestions can auto-execute via rules |
| 42 | E12 | Budget allocation AI + creative fatigue + saturation | Advanced optimization categories live |
| 43 | E12 | Performance prediction + cross-campaign learning | Prediction API working |
| 44 | E12 | Feedback loop + strategy simulation + cleanup cron | Learning system operational |
| 45 | All | Final integration testing + performance tuning | System ready for full production load |

## 6.3 Phase 3 Definition of Done

Users can create automation rules with trigger/condition/action config

Dry-run shows "would have triggered X times last week" before activation

Auto-execute mode works for budget/pause actions (with audit trail)

Require-approval mode queues for manager with 4-hour expiry

AI suggestions link to matching automation rules for auto-execution

Prediction accuracy tracked and visible in insight follow-ups

Weekly cleanup cron purges old metrics and archives audit log

# 7. Recommended Build Sequence for Claude-Driven Implementation

This section provides the optimal sequence for implementing features with Claude as the primary developer. It accounts for context window limitations, file dependencies, and the need for incremental testing.

## 7.1 Principles for Claude-Driven Development

One feature per session: Each Claude session should focus on a single feature (E1.1, E1.2, etc.). This keeps context tight and changes reviewable.

Read before write: Always start by reading the existing file that will be modified. Claude needs current state to make safe edits.

Test after each feature: Run TypeScript compilation check after each schema/service change. Run existing tests to catch regressions.

Commit after each feature: Git commit after each successful feature gives rollback safety.

Interface-first: Define TypeScript interfaces before implementation. This catches type errors early.

Scaffold then fill: Create file structure with stubs first, then implement one function at a time.

No big bang deploys: Each feature should be deployable independently (feature flags if needed).

## 7.2 Session-by-Session Build Plan

### Foundation Sessions (E1)

| Session | Task | Input Files (Read) | Output Files (Write/Edit) | Verification |
| --- | --- | --- | --- | --- |
| 1 | Extend Campaign + Lead interfaces | src/lib/db/schema.ts | src/lib/db/schema.ts (edit) | tsc --noEmit |
| 2 | Extend ClientKnowledge + ClientInsight + ClientFile | src/lib/db/schema.ts | src/lib/db/schema.ts (edit) | tsc --noEmit |
| 3 | Create Supabase migration: 6 new tables + indexes | (reference schema.ts) | supabase/migrations/[timestamp].sql | supabase db push (or review SQL) |
| 4 | Add SupabaseCrud instances + migrate automation_rules | src/lib/db/collections.ts | src/lib/db/collections.ts (edit) | tsc --noEmit; check imports |
| 5 | Create service stubs (12 files) | (reference architecture doc) | src/lib/services/*.ts (12 new files) | tsc --noEmit |
| 6 | Create EventBus + types + utility modules | (reference architecture doc) | src/lib/events/ + src/lib/utils/ | tsc --noEmit |

### Permissions Sessions (E2)

| Session | Task | Input Files | Output Files | Verification |
| --- | --- | --- | --- | --- |
| 7 | Define ROLE_PERMISSIONS matrix | src/lib/db/schema.ts (User type) | src/lib/auth/permissions.ts (new) | tsc --noEmit |
| 8 | Implement authorize() + checkResourceOwnership() | permissions.ts | src/lib/auth/authorize.ts (new) | tsc --noEmit |
| 9 | API middleware + cron/webhook auth | src/middleware.ts (if exists) | src/middleware.ts (edit/create) | Manual test: API returns 401/403 |
| 10 | AuditService implementation | Service stub from session 5 | src/lib/services/audit.service.ts (fill) | tsc --noEmit |
| 11 | Audit API routes + role migration script | audit.service.ts | src/app/api/audit/ + scripts/migrate-roles.ts | Test audit query; run migration dry-run |

### Connections Sessions (E3)

| Session | Task | Input Files | Output Files | Verification |
| --- | --- | --- | --- | --- |
| 12 | Base platform interface + Meta OAuth client | Platform docs reference | src/lib/platforms/base-platform.ts + meta/client.ts | tsc --noEmit |
| 13 | Google + TikTok + LinkedIn OAuth clients | base-platform.ts | src/lib/platforms/google/ + tiktok/ + linkedin/ | tsc --noEmit |
| 14 | ConnectionService implementation | Service stub + platform clients | src/lib/services/connection.service.ts (fill) | tsc --noEmit |
| 15 | Connection API routes | connection.service.ts | src/app/api/connections/ (all routes) | curl test: list connections |
| 16 | Connections UI screen + client tab | Existing UI patterns | src/app/(dashboard)/connections/ + TabConnections.tsx | Visual check |
| 17 | Connection health cron | connection.service.ts | src/app/api/cron/connection-health/ | curl test: cron endpoint |

### Campaign Sessions (E4)

| Session | Task | Input Files | Output Files | Verification |
| --- | --- | --- | --- | --- |
| 18 | CampaignService: CRUD + status machine | schema.ts + collections.ts | src/lib/services/campaign.service.ts (fill) | tsc --noEmit |
| 19 | CampaignService: publish + approval + audit | campaign.service.ts + platforms/ | src/lib/services/campaign.service.ts (extend) | tsc --noEmit |
| 20 | Campaign API routes (all) | campaign.service.ts | src/app/api/campaigns/ (all routes) | curl test: create/get campaign |
| 21 | Campaign Builder wizard UI (Steps 1-2) | Existing UI patterns | src/app/(dashboard)/campaigns/new/ | Visual check |
| 22 | Campaign Builder wizard UI (Steps 3-4) | Session 21 output | src/app/(dashboard)/campaigns/new/ (extend) | Visual check: complete flow |
| 23 | Campaign list + detail views | API routes | src/app/(dashboard)/campaigns/ + [id]/ | Visual check |
| 24 | Command Center update + client campaigns tab | Existing page.tsx | src/app/(dashboard)/page.tsx (edit) + TabCampaigns.tsx | Visual check |

### Metrics Sessions (E5)

| Session | Task | Input Files | Output Files | Verification |
| --- | --- | --- | --- | --- |
| 25 | MetricsService + Meta/Google normalization | Platform clients | src/lib/services/metrics.service.ts + platforms/*/metrics.ts | tsc --noEmit |
| 26 | TikTok/LinkedIn normalization + rate limiter | metrics.service.ts | platforms/tiktok/ + linkedin/ + rate-limiter.ts | tsc --noEmit |
| 27 | Metrics sync cron (cursor-based) | metrics.service.ts | src/app/api/cron/metrics-sync/ | curl test: sync runs |
| 28 | Health score computation + cron | campaign.service.ts | Health score logic + src/app/api/cron/health-scores/ | Test: score computes correctly |
| 29 | Metrics API + dashboard charts + vercel.json | All E5 code | src/app/api/campaigns/[id]/metrics/ + vercel.json | End-to-end: metrics visible |

### Leads Sessions (E6)

| Session | Task | Input Files | Output Files | Verification |
| --- | --- | --- | --- | --- |
| 30 | LeadService + dedup + normalize + platform extraction | schema.ts + platforms/ | src/lib/services/lead.service.ts + platforms/*/leads.ts | tsc --noEmit |
| 31 | Lead API routes + sync cron + Meta webhook | lead.service.ts | src/app/api/leads/ + cron/lead-sync/ + webhooks/ | curl test: webhook receives lead |
| 32 | Leads Kanban UI + drawer + funnel analytics | API routes | src/app/(dashboard)/leads/ + components/leads/ | Visual check: full lead flow |
| 33 | Lead export + client tab + MVP polish | lead.service.ts + existing TabLeads | Export endpoint + tab modifications | End-to-end: export downloads |

Sessions 34-45 follow the same pattern for Phase 2 and Phase 3 epics. Each session focuses on one feature, reads existing code first, edits incrementally, and verifies with tsc + manual test before committing.

## 7.3 Context Management Strategy

For Claude to be effective across sessions:

Keep a CLAUDE.md in the repo root with: architecture decisions, file map, current status, known issues.

Each session prompt should reference: "Read src/lib/db/schema.ts and src/lib/services/[relevant].ts before making changes."

After each session, update CLAUDE.md with what was built and any deviations from plan.

Use git diff as context: "Here's what changed in the last session: [paste diff summary]"

For complex features (Campaign Builder UI): split into sub-sessions focusing on one step/component at a time.

## 7.4 Prompt Templates for Claude Sessions

# Session prompt template:

## Context
We are building Campaign Intelligence for Frame-AI (Next.js + Supabase).
Current phase: [MVP/Phase2/Phase3], Epic: [E#], Feature: [E#.#]

## Existing Code (read first)
- [list files to read]

## Task
[Specific feature description from implementation plan]

## Constraints
- Do NOT modify existing interfaces (only extend)
- Use SupabaseCrud<T> pattern for all DB access
- Follow existing code style (check adjacent files)
- All new fields must be optional (backward compat)
- Use EventBus.emit() for cross-service communication
- Include AuditService.log() for all state changes

## Verification
After implementation: run `npx tsc --noEmit` and report any errors.

# 8. Risks & Integration Pitfalls

## 8.1 High-Priority Risks

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Schema extension breaks existing data | Critical — production data loss or app crash | Medium | All new fields MUST be optional (no NOT NULL without defaults). Test with existing data before deploy. |
| Platform API rate limits exceeded | High — metrics sync fails, data gaps | High | Implement rate limiter from day 1. Use cursor-based chunking. Respect per-platform quotas. Circuit breakers. |
| Vercel 60s timeout for background jobs | High — jobs fail mid-execution | Certain | Design ALL jobs with cursor-based resumption from the start. Never assume single-invocation completion. |
| OAuth token rotation failures | High — platform connections go dark | Medium | Auto-refresh before expiry (80% of TTL). Alert on refresh failure. Manual refresh button in UI. |
| OpenAI API instability | Medium — AI features unavailable | Low-Medium | Graceful degradation: system works without AI (just no insights). Retry with backoff. Model fallback (4o → 4o-mini). |
| Permission model too restrictive | Medium — team blocked from daily work | Medium | Start with permissive defaults. Monitor auth.permission_denied audit events. Quick role adjustment capability. |
| JSONB query performance at scale | Medium — slow dashboards at 500+ campaigns | Low | GIN indexes on key JSONB paths. Denormalize hot fields if needed. Monitor query latency. |
| Automation rules fire unexpectedly | High — unwanted campaign changes in production | Medium | Require dry-run before activation. Limit auto-execute scope. Undo capability within 5 min. |

## 8.2 Integration Pitfalls

### Pitfall 1: Modifying Existing Interfaces

The Campaign and Lead interfaces already have consumers across the codebase. Adding required fields will break TypeScript compilation everywhere they're used.

Rule: EVERY new field must use TypeScript optional syntax (?:). No exceptions.

// ✅ CORRECT: optional field
interface Campaign {
  // existing fields...
  healthScore?: number;  // NEW — optional
  platform?: string;     // NEW — optional
}

// ❌ WRONG: required field breaks all existing code
interface Campaign {
  healthScore: number;   // BREAKS: existing campaigns don't have this
}

### Pitfall 2: SupabaseCrud JSONB Queries

Filtering on nested JSONB fields requires specific Supabase query syntax. Standard .eq() doesn't work for nested paths.

// ✅ CORRECT: use arrow notation for JSONB path
supabase.from("app_campaigns").select("*")
  .eq("data->>clientId", clientId)
  .eq("data->>status", "active")

// ❌ WRONG: this queries a top-level column that doesn't exist
supabase.from("app_campaigns").select("*")
  .eq("clientId", clientId)

### Pitfall 3: Client Detail Page Tab Array

The client detail page uses a hardcoded TABS array. Adding new tabs requires modifying this array AND adding the conditional render block. Missing either breaks the tab.

// In src/app/(dashboard)/clients/[id]/page.tsx
// MUST add to BOTH the TABS array AND the render section:

// 1. Add to TABS array:
const TABS = [
  // ...existing tabs...
  { id: "campaigns", label: "קמפיינים" },  // NEW
  { id: "competitor", label: "מתחרים" },    // NEW
];

// 2. Add render block:
{activeTab === "campaigns" && <TabCampaigns client={client} />}
{activeTab === "competitor" && <TabCompetitors client={client} />}

### Pitfall 4: JsonStore vs SupabaseCrud Confusion

The codebase has ~19 JsonStore collections (file-based, ephemeral on Vercel) and 16 SupabaseCrud collections. Campaign Intelligence must use SupabaseCrud for ALL new data. Never use JsonStore for persistent data.

Rule: All new collections use SupabaseCrud<T>. The only acceptable use of JsonStore is for cache/temp data that can be regenerated.

### Pitfall 5: useData Hook Patterns

The frontend uses useData<T> hook for data fetching. New pages must follow the same pattern for consistency and to benefit from refetchOnFocus behavior.

// Follow this pattern for all new pages:
const { data: campaigns, loading, error, refetch } = useData<Campaign[]>(
  "/api/campaigns",
  { params: { clientId, status: "active" } }
);

// NOT: fetch() or axios or useSWR or useEffect+setState

### Pitfall 6: Vercel Cron Authentication

Vercel cron jobs hit your API routes from Vercel's infrastructure. Without auth checking, anyone could hit /api/cron/metrics-sync directly. But session auth won't work (no browser).

// Cron routes MUST check CRON_SECRET:
export async function GET(req: Request) {
  const authHeader = req.headers.get("authorization");
  if (authHeader !== `Bearer ${process.env.CRON_SECRET}`) {
    return new Response("Unauthorized", { status: 401 });
  }
  // ... cron logic ...
}

### Pitfall 7: Event Ordering and Race Conditions

With EventBus, multiple handlers fire on the same event. If handler A writes to DB and handler B reads, the read may get stale data if they run concurrently.

Rule: Critical handlers use await (sequential). Non-critical handlers (notifications, audit) fire async. Order in EventBus is deterministic within a single handler chain.

### Pitfall 8: Hebrew/RTL in Reports and UI

The existing system uses Hebrew extensively. New UI components and reports must support RTL layout. Failing to set dir="rtl" results in broken alignment.

Rule: All new pages inherit the app-level RTL from the existing layout. Report templates explicitly set direction. Tab labels use Hebrew per existing convention.

## 8.3 Risk Monitoring

Track these metrics weekly during implementation:

| Metric | Target | Alert If |
| --- | --- | --- |
| TypeScript compilation errors | 0 | > 0 (blocking) |
| Existing test pass rate | 100% | < 100% (blocking) |
| API response time (p95) | < 500ms | > 1000ms |
| Cron job completion rate | > 99% | < 95% |
| Platform API error rate | < 5% | > 10% |
| Audit log events/day | > 50 (shows usage) | < 10 (audit may be broken) |
| Permission denied events/day | < 10 | > 50 (roles too restrictive) |

# 9. What Must Be Implemented First to Avoid Breaking Production

## 9.1 Non-Negotiable Prerequisites (Before ANY Feature Work)

### Prerequisite 1: Schema Extensions Must Be Additive Only

Before modifying src/lib/db/schema.ts, ensure no existing code will break. This means searching the codebase for every usage of Campaign, Lead, ClientKnowledge, etc. and confirming new fields are optional.

# Safety check before schema changes:
grep -rn "Campaign" src/ --include="*.ts" --include="*.tsx" | wc -l
grep -rn "Lead" src/ --include="*.ts" --include="*.tsx" | wc -l
# Review each usage to confirm optional fields won't cause type errors

### Prerequisite 2: Database Migration Must Be Reversible

Every Supabase migration should have a corresponding down migration. New tables can simply be dropped. Extended tables (if any) need the columns to be removed cleanly.

-- up migration (new tables only — no ALTER on existing tables)
CREATE TABLE IF NOT EXISTS app_campaign_metrics (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  data JSONB NOT NULL DEFAULT '{}'::jsonb,
  created_at TIMESTAMPTZ DEFAULT NOW(),
  updated_at TIMESTAMPTZ DEFAULT NOW()
);

-- down migration
DROP TABLE IF EXISTS app_campaign_metrics;

### Prerequisite 3: Permission System Must Have Fallback

The new permission system must not lock out existing users. Before full rollout, implement a PERMISSIVE_MODE flag that logs permission checks but doesn't enforce them. Once confirmed working, switch to ENFORCING mode.

const PERMISSION_MODE = process.env.PERMISSION_MODE || "permissive";

export async function authorize(user, action, resource) {
  const allowed = checkPermission(user, action, resource);
  
  if (!allowed) {
    await AuditService.log({ action: "auth.permission_denied", ... });
    
    if (PERMISSION_MODE === "enforcing") {
      throw new ForbiddenError(action);
    }
    // In permissive mode: log but allow (for testing)
    console.warn(`[PERMISSIVE] Would deny: ${user.role} → ${action}`);
  }
}

### Prerequisite 4: Legacy Role Mapping Day 1

The getLegacyRole() function MUST exist before any permission code is deployed. Any existing code that checks role === "admin" or "manager" must continue to work unchanged.

## 9.2 Implementation Safety Order

This is the strict order for the first week of development. Do not skip steps.

| Order | Action | Verification | Rollback Plan |
| --- | --- | --- | --- |
| 1 | Add new tables (migration UP only) | Tables exist; no impact on existing tables | DROP TABLE IF EXISTS (all 6) |
| 2 | Add indexes on new tables | Indexes exist | DROP INDEX IF EXISTS |
| 3 | Add SupabaseCrud instances for new tables | Import works; existing crud unchanged | Remove new crud lines from collections.ts |
| 4 | Extend interfaces with OPTIONAL fields only | tsc --noEmit passes; no type errors | Revert schema.ts to previous version |
| 5 | Add getLegacyRole() utility | Existing auth code still works | Remove function (no callers yet) |
| 6 | Add authorize() in PERMISSIVE mode | Logs show permission checks; nothing blocked | Set PERMISSIVE forever or remove |
| 7 | Add audit service (writes only) | Audit records appear in new table | Remove audit calls (no external impact) |
| 8 | Add service stubs (empty functions) | tsc passes; no runtime impact | Delete new files |
| 9 | Add EventBus (no subscribers yet) | No runtime impact | Delete event files |
| 10 | Migrate automation_rules (copy, not move) | Both old and new store have data | Delete new table data; old store unaffected |

## 9.3 Feature Flags

Use feature flags to control visibility of new features during development. This allows shipping code to production without exposing incomplete features to users.

// src/lib/feature-flags.ts
export const FEATURES = {
  CAMPAIGN_INTELLIGENCE: process.env.NEXT_PUBLIC_FF_CAMPAIGN_INTEL === "true",
  AI_INSIGHTS: process.env.NEXT_PUBLIC_FF_AI_INSIGHTS === "true",
  AUTOMATIONS: process.env.NEXT_PUBLIC_FF_AUTOMATIONS === "true",
  COMPETITOR_INTEL: process.env.NEXT_PUBLIC_FF_COMPETITOR === "true",
};

// Usage in UI:
{FEATURES.CAMPAIGN_INTELLIGENCE && (
  <NavItem href="/campaigns" label="קמפיינים" />
)}

// Usage in API routes:
if (!FEATURES.CAMPAIGN_INTELLIGENCE) {
  return new Response("Feature not enabled", { status: 404 });
}

## 9.4 Deployment Strategy

| Phase | Deployment | Audience | Rollback |
| --- | --- | --- | --- |
| Development | Preview deployments (Vercel preview) | Dev team only | Redeploy previous commit |
| MVP Internal | Production with FF=true for team only | Internal team | Set FF=false |
| MVP Beta | Production with FF=true for all internal users | All agency staff | Set FF=false |
| GA | Production, FF removed, fully live | All users + clients | Revert to FF-guarded commit |

## 9.5 Existing Files That Must NOT Be Broken

These files have the highest blast radius if modified incorrectly:

| File | Risk If Broken | Safe Modification Pattern |
| --- | --- | --- |
| src/lib/db/schema.ts | All TypeScript fails to compile | Only ADD optional fields; never remove or make required |
| src/lib/db/collections.ts | All data access fails | Only ADD new crud/store instances; never modify existing |
| src/app/(dashboard)/clients/[id]/page.tsx | Client detail page breaks for all users | Only add to TABS array + add conditional render; don't restructure |
| src/middleware.ts | All API routes may become inaccessible | Add new checks AFTER existing checks; test extensively |
| src/app/(dashboard)/page.tsx | Dashboard breaks for all users | Add new sections below existing; feature-flag new content |
| src/lib/db/supabase-crud.ts | ALL data operations break | DO NOT MODIFY. Use composition, not inheritance. |
| package.json | Build fails if bad dependency | Only add dependencies; never modify existing versions |

## 9.6 Final Checklist Before Each Deploy

npx tsc --noEmit passes with 0 errors

Existing tests pass (if test suite exists)

No modifications to existing interface required fields

New SupabaseCrud instances don't conflict with existing table names

Feature flags gate all new UI

Cron routes check CRON_SECRET

Permission mode is "permissive" until explicitly switched

Audit logging is active for all new operations

New tabs use Hebrew labels consistent with existing UI

Git diff reviewed: no unintended changes to existing files